## Project_Info
TIO2 SPRINT INTELLIGENCE · PROJECT INFORMATION
Project Name | Sponsor | Business Unit | Project Manager | Start Date | Target End Date | Sprint Length (Days) | Methodology | Customer | Status
TIO2 – Telematics Gateway ECU Modernization | Dr. Klaus Bergmann | Commercial Vehicles | Suresh Iyer | 2026-04-21 | 2026-08-13 | 14 | Agile Scrum | Daimler Truck | Active
KEY PROJECT METRICS
Total Sprints | 8
Sprint Length (days) | 14
Target Confidence Level | 80%
Current Sprint | 6
Sprints Completed | 5
Sprints Remaining | 2
Total Team Size | 9
Technology Domain | Automotive Embedded Software
Compliance Target | MISRA C:2012, ASPICE L2
Release Cadence | 45-Day Delivery Cycle

## Team
TIO2 – TEAM RESOURCE REGISTER
Resource Name | Role | Skill 1 | Skill 1 Level | Skill 2 | Skill 2 Level | Skill 3 | Skill 3 Level | S1 Alloc % | S1 Avail % | S2 Alloc % | S2 Avail % | S3 Alloc % | S3 Avail % | S4 Alloc % | S4 Avail % | S5 Alloc % | S5 Avail % | S6 Alloc % | S6 Avail % | S7 Alloc % | S7 Avail % | S8 Alloc % | S8 Avail %
Karthik Subramaniam | Technical Lead / AUTOSAR Architect | AUTOSAR Stack Configuration | L1-Expert | MCAL Driver Integration | L2-Advanced | OS Task Scheduling | L2-Advanced | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% |  | 100%
Priya Meenakshi | Senior CAN / Protocols Engineer | CAN / J1939 Protocol Development | L1-Expert | COM Stack & Signal Mapping | L2-Advanced | CANoe Scripting | L3-Intermediate | 80% | 100% | 80% | 100% | 80% | 100% | 80% | 100% | 80% | 100% | 80% |  | 80% |  | 80%
Arjun Sundaram | Diagnostics Engineer | UDS Diagnostics & DTC Management | L1-Expert | DCM / DEM Module Configuration | L2-Advanced | ASPICE Audit Support | L3-Intermediate | 100% | 100% | 100% | 100% | 100% | 80% | 100% | 80% | 100% | 100% | 100% |  | 100% |  | 100%
Vikram Narayanan | System Architect / Integration Lead | ECU Integration & Gateway Routing | L1-Expert | PDU Configuration | L2-Advanced | Fleet Telemetry | L2-Advanced | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% |  | 100%
Akshaya Krishnan | Test Engineer | HIL Testing & CANoe Automation | L2-Advanced | Regression & Integration Testing | L2-Advanced | OTA Validation | L3-Intermediate | 70% | 100% | 70% | 100% | 50% | 100% | 70% | 100% | 70% | 70% | 70% |  | 70% |  | 70%
Sandeep Annamalai | Cybersecurity Engineer | Automotive Cybersecurity (EVITA) | L2-Advanced | SecOC & Secure Boot | L2-Advanced | HSM Integration | L3-Intermediate | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 40% | 80% |  | 80% |  | 80%
Divya Rajalakshmi | Scrum Master | Agile Delivery & Sprint Tracking | L1-Expert | Stakeholder Communication | L2-Advanced | DoD Governance | L2-Advanced | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% |  | 100%
Meena Balasubramanian | OTA / Firmware Engineer | OTA Firmware Update Mechanisms | L2-Advanced | Manifest & Delta Packaging | L3-Intermediate | Backend API Integration | L4-Beginner | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% |  | 100%
Ravi Chandran | Junior Test / Integration Engineer | Regression & Integration Testing | L3-Intermediate | HIL Testing & CANoe Automation | L4-Beginner | OTA Validation | L4-Beginner | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% |  | 100%
Skill Levels: L1=Expert ¦ L2=Advanced ¦ L3=Intermediate ¦ L4=Beginner

## Sprint_Plan
TIO2 – SPRINT PLAN
Sprint Name | Start Date | End Date | Duration (Days) | Sprint Goal | Status | Velocity (h) | Carry-Over Items
Sprint 1 | 2026-04-21 | 2026-05-04 | 14 | Platform Setup — dev environment, ETAS ISOLAR-A/B toolchain, AUTOSAR BSW baseline (MICROSAR), CAN driver scaffolding, ECU HAL init, OS task scheduling, CI pipeline. | Completed | 253 | 1
Sprint 2 | 2026-05-05 | 2026-05-18 | 14 | CAN Communication — J1939 stack, CAN frame routing, signal mapping, PDU configuration, gateway routing table, CANoe test harness, address claiming. | Completed | 229 | 1
Sprint 3 | 2026-05-19 | 2026-06-01 | 14 | Diagnostics — UDS services (0x10/0x19/0x22/0x27/0x2E), DTC management, session control. New joiner (Ravi) onboarded. BLK-001 OEM spec blocker caused partial rework on UDS. | Completed | 271 | 1
Sprint 4 | 2026-06-02 | 2026-06-15 | 14 | AUTOSAR Integration — RTE generation, SWC mapping, MCAL (SPI/LIN/Eth), DCM/DEM, COM signal routing, NvM. COM stack rework loop. BLK-003 HW bench blocked 3 WIs (rescheduled to S5). | Completed | 256 | 3
Sprint 5 | 2026-06-16 | 2026-06-29 | 14 | Cybersecurity — SecOC, HSM key mgmt, secure boot, TLS 1.3, EVITA HSM driver, IDS. Sandeep sick leave (8 days). 2 WIs carried to S6. BLK-004 (Daimler API) open. | Completed | 347 | 2
Sprint 6 | 2026-06-30 | 2026-07-13 | 14 | OTA Updates — delta packaging, session manager, rollback, manifest validation. BLK-004 resolution critical. TLS 1.3 + IDS carry-overs from S5. | In Progress | 0 | 0
Sprint 7 | 2026-07-14 | 2026-07-27 | 14 | System Integration — E2E HIL bench, gateway routing validation, CAN+UDS+OTA regression, telemetry signal validation on target HW. | Not Started | 0 | 0
Sprint 8 | 2026-07-28 | 2026-08-10 | 14 | Release Readiness — FOTA E2E, MISRA C:2012 compliance, ASPICE L2 docs, Daimler Truck sign-off. | Not Started | 0 | 0

## Work_Items
TIO2 – WORK ITEM REGISTER (Sprint Backlog & Actuals)
Task ID | Task Name | Type | Sprint | Orig. Sprint | Owner | Required Skill | Priority | Orig Est (h) | Curr Est (h) | Actual Hrs | Remaining Hrs | Progress % | Status | Scope Change | Scope Reason
WI-001 | AUTOSAR BSW Baseline Configuration | Feature | Sprint 1 | Sprint 1 | Karthik Subramaniam | AUTOSAR Stack Configuration | High | 40 | 48 | 50 | 0 | 100% | Completed | Yes | Technical Debt
WI-002 | Development Toolchain Setup (ETAS ISOLAR-A/B) | Task | Sprint 1 | Sprint 1 | Vikram Narayanan | ECU Integration & Gateway Routing | High | 16 | 16 | 19 | 0 | 100% | Completed | No
WI-003 | CAN Driver Scaffolding | Story | Sprint 1 | Sprint 1 | Priya Meenakshi | CAN / J1939 Protocol Development | High | 24 | 28 | 30 | 0 | 100% | Completed | Yes | Technical Debt
WI-004 | ECU Hardware Abstraction Layer (MCAL Init) | Feature | Sprint 1 | Sprint 1 | Karthik Subramaniam | MCAL Driver Integration | High | 32 | 36 | 38 | 0 | 100% | Completed | Yes | Customer Request
WI-005 | CANoe Test Environment Setup | Task | Sprint 1 | Sprint 1 | Akshaya Krishnan | HIL Testing & CANoe Automation | Medium | 12 | 12 | 13 | 0 | 100% | Completed | No
WI-006 | AUTOSAR OS Task Scheduling Configuration | Story | Sprint 1 | Sprint 1 | Karthik Subramaniam | AUTOSAR Stack Configuration | High | 20 | 24 | 25 | 0 | 100% | Completed | Yes | Technical Debt
WI-007 | Spike: Evaluate ETAS RTA-OS vs MICROSAR OS | Spike | Sprint 1 | Sprint 1 | Vikram Narayanan | ECU Integration & Gateway Routing | High | 16 | 16 | 17 | 0 | 100% | Completed | No
WI-008 | COM Stack Initial Configuration | Story | Sprint 1 | Sprint 1 | Priya Meenakshi | COM Stack & Signal Mapping | Medium | 16 | 20 | 32 | 0 | 100% | Completed | Yes | Enhancement
WI-009 | Version Control & CI Pipeline Setup | Task | Sprint 1 | Sprint 1 | Sandeep Annamalai | Automotive Cybersecurity (EVITA) | Medium | 12 | 12 | 21 | 0 | 100% | Completed | No
WI-010 | Sprint 1 Definition of Done Review | Task | Sprint 1 | Sprint 1 | Divya Rajalakshmi | Agile Delivery & Sprint Tracking | Low | 8 | 8 | 8 | 0 | 100% | Completed | No
WI-011 | J1939 Protocol Stack Integration | Feature | Sprint 2 | Sprint 2 | Priya Meenakshi | CAN / J1939 Protocol Development | High | 40 | 48 | 50 | 0 | 100% | Completed | Yes | Customer Request
WI-012 | CAN Frame Routing Logic Implementation | Feature | Sprint 2 | Sprint 2 | Priya Meenakshi | CAN / J1939 Protocol Development | High | 32 | 36 | 37 | 0 | 100% | Completed | Yes | Technical Debt
WI-013 | Signal Mapping & PDU Configuration | Story | Sprint 2 | Sprint 2 | Vikram Narayanan | PDU Configuration | High | 24 | 24 | 25 | 0 | 100% | Completed | No
WI-014 | CAN Gateway Routing Table Configuration | Story | Sprint 2 | Sprint 2 | Vikram Narayanan | ECU Integration & Gateway Routing | High | 20 | 26 | 27 | 0 | 100% | Completed | Yes | Customer Request
WI-015 | CANoe Automated Test Harness (CAN Layer) | Task | Sprint 2 | Sprint 2 | Akshaya Krishnan | HIL Testing & CANoe Automation | Medium | 20 | 20 | 21 | 0 | 100% | Completed | No
WI-016 | Spike: CAN FD Feasibility for High-BW Signals | Spike | Sprint 2 | Sprint 2 | Vikram Narayanan | ECU Integration & Gateway Routing | Medium | 12 | 12 | 12 | 0 | 100% | Completed | No
WI-017 | CAN Bus Error Handling & Fault Injection Tests | Story | Sprint 2 | Sprint 2 | Akshaya Krishnan | HIL Testing & CANoe Automation | Medium | 16 | 20 | 20 | 0 | 100% | Completed | No
WI-018 | J1939 Address Claiming Procedure | Story | Sprint 2 | Sprint 2 | Priya Meenakshi | CAN / J1939 Protocol Development | High | 16 | 16 | 17 | 0 | 100% | Completed | Yes | Regulatory
WI-019 | [CO-S1] Fleet Telemetry Preliminary Design | Story | Sprint 2 | Sprint 1 | Vikram Narayanan | ECU Integration & Gateway Routing | Medium | 16 | 20 | 20 | 0 | 100% | Completed | No
WI-020 | UDS Service 0x10 – Diagnostic Session Control | Feature | Sprint 3 | Sprint 3 | Arjun Sundaram | UDS Diagnostics & DTC Management | High | 24 | 28 | 31 | 0 | 100% | Completed | No
WI-021 | UDS Service 0x27 – Security Access | Feature | Sprint 3 | Sprint 3 | Arjun Sundaram | UDS Diagnostics & DTC Management | High | 20 | 24 | 27 | 0 | 100% | Completed | Yes | Technical Debt
WI-022 | UDS Service 0x19 – Read DTC Information | Feature | Sprint 3 | Sprint 3 | Arjun Sundaram | UDS Diagnostics & DTC Management | High | 24 | 30 | 38 | 0 | 100% | Completed | Yes | Customer Request
WI-023 | DTC Management – Fault Storage & Ageing | Story | Sprint 3 | Sprint 3 | Arjun Sundaram | UDS Diagnostics & DTC Management | High | 20 | 24 | 26 | 0 | 100% | Completed | No
WI-024 | UDS Service 0x22/0x2E – Data Identifier R/W | Story | Sprint 3 | Sprint 3 | Arjun Sundaram | UDS Diagnostics & DTC Management | High | 16 | 20 | 22 | 0 | 100% | Completed | Yes | Enhancement
WI-025 | Diagnostic Logging Module | Story | Sprint 3 | Sprint 3 | Karthik Subramaniam | AUTOSAR Stack Configuration | Medium | 16 | 16 | 17 | 0 | 100% | Completed | No
WI-026 | CANoe Diagnostic Test Script (KWP/UDS) | Task | Sprint 3 | Sprint 3 | Akshaya Krishnan | CANoe Scripting | Medium | 16 | 20 | 38 | 0 | 100% | Completed | No
WI-027 | Defect: UDS 0x10 Session Timeout Not Honoured | Defect | Sprint 3 | Sprint 3 | Arjun Sundaram | UDS Diagnostics & DTC Management | High | 8 | 8 | 10 | 0 | 100% | Completed | No
WI-028 | [CO-S2] COM Stack PDU Routing Hardening | Story | Sprint 3 | Sprint 2 | Priya Meenakshi | COM Stack & Signal Mapping | Medium | 16 | 20 | 22 | 0 | 100% | Completed | No
WI-029 | Knowledge Transfer: Ravi Chandran Onboarding | Task | Sprint 3 | Sprint 3 | Akshaya Krishnan | HIL Testing & CANoe Automation | Medium | 0 | 40 | 40 | 0 | 100% | Completed | Yes | Other
WI-030 | AUTOSAR RTE Generation & SWC Port Mapping | Feature | Sprint 4 | Sprint 4 | Karthik Subramaniam | AUTOSAR Stack Configuration | High | 40 | 52 | 54 | 0 | 100% | Completed | Yes | Customer Request
WI-031 | MCAL Driver Integration (SPI, LIN, Ethernet) | Feature | Sprint 4 | Sprint 4 | Karthik Subramaniam | MCAL Driver Integration | High | 32 | 38 | 40 | 0 | 100% | Completed | No
WI-032 | Diagnostic Session Manager Refactor | Story | Sprint 4 | Sprint 3 | Arjun Sundaram | DCM / DEM Module Configuration | High | 16 | 22 | 26 | 0 | 100% | Completed | No
WI-033 | COM Stack Signal Routing Rework | Defect | Sprint 4 | Sprint 4 | Priya Meenakshi | COM Stack & Signal Mapping | High | 0 | 18 | 18 | 0 | 100% | Completed | Yes | Defect
WI-034 | DCM Module Configuration & Session Handling | Story | Sprint 4 | Sprint 4 | Meena Balasubramanian | DCM / DEM Module Configuration | High | 20 | 24 | 36 | 0 | 100% | Completed | No
WI-035 | DEM Module Configuration & Event Handling | Story | Sprint 4 | Sprint 4 | Arjun Sundaram | DCM / DEM Module Configuration | High | 20 | 24 | 25 | 0 | 100% | Completed | No
WI-036 | NvM Module – Non-Volatile Storage Configuration | Story | Sprint 4 | Sprint 4 | Karthik Subramaniam | AUTOSAR Stack Configuration | Medium | 16 | 20 | 21 | 0 | 100% | Completed | No
WI-037 | AUTOSAR Integration Test – RTE Scheduler (Shadow) | Task | Sprint 4 | Sprint 4 | Ravi Chandran | HIL Testing & CANoe Automation | Medium | 16 | 16 | 28 | 0 | 100% | Completed | No
WI-038 | Sprint 4 DoD Review | Task | Sprint 4 | Sprint 4 | Divya Rajalakshmi | Agile Delivery & Sprint Tracking | Low | 8 | 8 | 8 | 0 | 100% | Completed | No
WI-039 | Gateway ECU Board Support Package Validation | Feature | Sprint 5 | Sprint 4 | Vikram Narayanan | ECU Integration & Gateway Routing | High | 28 | 36 | 38 | 0 | 100% | Completed | No
WI-040 | Memory Footprint Analysis & Stack Profiling | Task | Sprint 5 | Sprint 4 | Karthik Subramaniam | AUTOSAR Stack Configuration | Medium | 12 | 16 | 17 | 0 | 100% | Completed | No
WI-041 | Defect: RTE Runnable Period Drift Under Load | Defect | Sprint 5 | Sprint 4 | Karthik Subramaniam | AUTOSAR Stack Configuration | High | 12 | 12 | 14 | 0 | 100% | Completed | No
WI-044 | SecOC Module Implementation | Feature | Sprint 5 | Sprint 5 | Sandeep Annamalai | SecOC & Secure Boot | High | 40 | 44 | 58 | 0 | 100% | Completed | No
WI-045 | HSM Key Management & Certificate Provisioning | Feature | Sprint 5 | Sprint 5 | Sandeep Annamalai | Automotive Cybersecurity (EVITA) | High | 36 | 44 | 52 | 0 | 100% | Completed | Yes | Customer Request
WI-046 | Secure Boot Chain Verification | Story | Sprint 5 | Sprint 5 | Sandeep Annamalai | SecOC & Secure Boot | High | 24 | 28 | 32 | 0 | 100% | Completed | No
WI-047 | TLS 1.3 for Backend Communication | Story | Sprint 6 | Sprint 5 | Sandeep Annamalai | Automotive Cybersecurity (EVITA) | High | 28 | 32 | 0 | 32 | 0% | Not Started | No
WI-048 | Cybersecurity Test Plan & Attack Surface Analysis | Task | Sprint 5 | Sprint 5 | Ravi Chandran | HIL Testing & CANoe Automation | High | 20 | 20 | 39 | 0 | 100% | Completed | No
WI-049 | EVITA HSM Driver Integration | Story | Sprint 5 | Sprint 5 | Sandeep Annamalai | Automotive Cybersecurity (EVITA) | High | 20 | 24 | 26 | 0 | 100% | Completed | No
WI-050 | IDS Configuration | Story | Sprint 6 | Sprint 5 | Sandeep Annamalai | Automotive Cybersecurity (EVITA) | Medium | 16 | 20 | 0 | 20 | 0% | Not Started | No
WI-056 | OTA Backend API Integration Prototype | Story | Sprint 5 | Sprint 5 | Meena Balasubramanian | Backend API Integration | Medium | 20 | 24 | 41 | 0 | 100% | Completed | No
WI-051 | Spike: Adaptive AUTOSAR vs Classic for OTA Path | Spike | Sprint 5 | Sprint 5 | Vikram Narayanan | ECU Integration & Gateway Routing | High | 16 | 20 | 21 | 0 | 100% | Completed | No
WI-052 | Sprint 5 DoD Review | Task | Sprint 5 | Sprint 5 | Divya Rajalakshmi | Agile Delivery & Sprint Tracking | Low | 8 | 8 | 9 | 0 | 100% | Completed | No
WI-053 | OTA Session Manager Implementation | Feature | Sprint 6 | Sprint 6 | Meena Balasubramanian | OTA Firmware Update Mechanisms | High | 36 | 40 | 0 | 40 | 0% | Not Started | No
WI-054 | Firmware Delta Packaging Tool | Feature | Sprint 6 | Sprint 6 | Meena Balasubramanian | Manifest & Delta Packaging | High | 32 | 32 | 0 | 32 | 0% | Not Started | No
WI-055 | OTA Rollback & Recovery Logic | Story | Sprint 6 | Sprint 6 | Meena Balasubramanian | OTA Firmware Update Mechanisms | High | 24 | 28 | 0 | 28 | 0% | Not Started | No
WI-057 | Manifest Validation & Signature Verification | Story | Sprint 6 | Sprint 6 | Sandeep Annamalai | Manifest & Delta Packaging | High | 20 | 24 | 0 | 24 | 0% | Not Started | No
WI-058 | OTA Progress Reporting to Fleet Backend | Story | Sprint 6 | Sprint 6 | Meena Balasubramanian | OTA Firmware Update Mechanisms | Medium | 16 | 20 | 0 | 20 | 0% | Not Started | No
WI-059 | Spike: Delta Compression Algorithm Evaluation | Spike | Sprint 6 | Sprint 6 | Meena Balasubramanian | Manifest & Delta Packaging | Medium | 16 | 16 | 0 | 16 | 0% | Not Started | No
WI-060 | Sprint 6 DoD Review | Task | Sprint 6 | Sprint 6 | Divya Rajalakshmi | Agile Delivery & Sprint Tracking | Low | 8 | 8 | 0 | 8 | 0% | Not Started | No
WI-061 | End-to-End HIL Bench Integration Test | Feature | Sprint 7 | Sprint 7 | Akshaya Krishnan | HIL Testing & CANoe Automation | High | 48 | 56 | 0 | 56 | 0% | Not Started | No
WI-062 | Gateway Routing End-to-End Validation | Feature | Sprint 7 | Sprint 7 | Vikram Narayanan | ECU Integration & Gateway Routing | High | 36 | 36 | 0 | 36 | 0% | Not Started | No
WI-063 | CAN + UDS + OTA Regression Test Suite | Task | Sprint 7 | Sprint 7 | Akshaya Krishnan | Regression & Integration Testing | High | 32 | 36 | 0 | 36 | 0% | Not Started | No
WI-064 | Vehicle Telemetry Signal Validation on Target | Story | Sprint 7 | Sprint 7 | Vikram Narayanan | ECU Integration & Gateway Routing | High | 24 | 28 | 0 | 28 | 0% | Not Started | No
WI-065 | HIL OTA Update Cycle Validation | Task | Sprint 7 | Sprint 7 | Ravi Chandran | HIL Testing & CANoe Automation | High | 20 | 20 | 0 | 20 | 0% | Not Started | No
WI-066 | Sprint 7 DoD Review | Task | Sprint 7 | Sprint 7 | Divya Rajalakshmi | Agile Delivery & Sprint Tracking | Low | 8 | 8 | 0 | 8 | 0% | Not Started | No
WI-067 | Final MISRA C:2012 Compliance Review & Waivers | Feature | Sprint 8 | Sprint 8 | Karthik Subramaniam | AUTOSAR Stack Configuration | High | 32 | 36 | 0 | 36 | 0% | Not Started | No
WI-068 | ASPICE L2 Audit Documentation Package | Feature | Sprint 8 | Sprint 8 | Divya Rajalakshmi | Agile Delivery & Sprint Tracking | High | 24 | 28 | 0 | 28 | 0% | Not Started | No
WI-069 | FOTA End-to-End System Validation | Feature | Sprint 8 | Sprint 8 | Meena Balasubramanian | OTA Firmware Update Mechanisms | High | 28 | 32 | 0 | 32 | 0% | Not Started | No
WI-070 | Customer Sign-Off Demo – Daimler Truck | Task | Sprint 8 | Sprint 8 | Vikram Narayanan | ECU Integration & Gateway Routing | High | 16 | 16 | 0 | 16 | 0% | Not Started | No
WI-071 | Release Notes & Configuration Baseline Lock | Task | Sprint 8 | Sprint 8 | Karthik Subramaniam | AUTOSAR Stack Configuration | Medium | 12 | 12 | 0 | 12 | 0% | Not Started | No
WI-072 | Sprint 8 DoD Review & Project Retrospective | Task | Sprint 8 | Sprint 8 | Divya Rajalakshmi | Agile Delivery & Sprint Tracking | Low | 8 | 8 | 0 | 8 | 0% | Not Started | No
TOTALS | [7 empty] | 1706 | 1356 | 536
WI-073 | CAN Bus Signal Verification (Regression) | Task | Sprint 3 | Sprint 3 | Ravi Chandran | HIL Testing & CANoe Automation | Medium | 12 | 12 | 19 | 0 | 1 | Completed | No

## Dependencies
TIO2 – DEPENDENCY REGISTER (Critical Path & Lag Analysis)
Dep ID | Predecessor Task | Successor Task | Dependency Type | Lag Days
DEP-001 | WI-001 | WI-003 | Finish-To-Start | 0
DEP-002 | WI-001 | WI-004 | Finish-To-Start | 0
DEP-003 | WI-003 | WI-011 | Finish-To-Start | 0
DEP-004 | WI-003 | WI-013 | Finish-To-Start | 0
DEP-005 | WI-011 | WI-020 | Finish-To-Start | 0
DEP-006 | WI-023 | WI-025 | Finish-To-Start | 0
DEP-007 | WI-004 | WI-030 | Finish-To-Start | 0
DEP-008 | WI-020 | WI-034 | Finish-To-Start | 0
DEP-009 | WI-030 | WI-044 | Finish-To-Start | 1
DEP-010 | WI-045 | WI-046 | Finish-To-Start | 2
DEP-011 | WI-046 | WI-053 | Finish-To-Start | 2
DEP-012 | WI-053 | WI-057 | Finish-To-Start | 1
DEP-013 | WI-065 | WI-061 | Finish-To-Start | 1
DEP-014 | WI-061 | WI-067 | Finish-To-Start | 0
DEP-015 | WI-025 | WI-039 | Finish-To-Start | 0
DEP-016 | WI-013 | WI-033 | Finish-To-Start | 0
DEP-017 | WI-033 | WI-041 | Finish-To-Start | 0
DEP-018 | WI-053 | WI-062 | Finish-To-Start | 1
DEP-019 | WI-059 | WI-054 | Finish-To-Start | 0
DEP-020 | WI-055 | WI-069 | Finish-To-Start | 1
DEP-021 | WI-047 | WI-056 | Finish-To-Start | 0
DEP-022 | WI-028 | WI-033 | Finish-To-Start | 0
DEP-023 | WI-032 | WI-035 | Finish-To-Start | 0
DEP-024 | WI-054 | WI-062 | Finish-To-Start | 0
DEP-025 | WI-057 | WI-062 | Finish-To-Start | 0

## Blockers
TIO2 – BLOCKER REGISTER
Blocker ID | Related Task | Impacted Task IDs | Severity | Status | Owner | Raised Date | Target Resolution | Actual Resolution | Category | Sprint Identified | Notes
BLK-001 | WI-022 | WI-022, WI-027, WI-040 | Critical | Resolved | Arjun Sundaram | 2026-05-19 | 2026-05-28 | 2026-05-29 | External Team Dependency | Sprint 3 | OEM spec for UDS 0x19 arrived late; forced partial rework on DTC read services. Resolved after OEM clarification.
BLK-002 | WI-015 | WI-015, WI-017, WI-026 | High | Resolved | Akshaya Krishnan | 2026-05-05 | 2026-05-14 | 2026-05-13 | Tool Issue | Sprint 2 | CANoe license server outage blocked CAN automated tests. Vendor issued temp license to unblock.
BLK-003 | WI-039 | WI-039, WI-040, WI-041 | High | Resolved | Vikram Narayanan | 2026-06-01 | 2026-06-10 | 2026-06-10 | Lab Issue | Sprint 3 | HIL bench hardware unavailable due to lab procurement delay. WI-039/040/041 rescheduled to S5.
BLK-004 | WI-056 | WI-058 | High | Open | Meena Balasubramanian | 2026-06-16 | 2026-06-25 | Open | External Team Dependency | Sprint 5 | Daimler API credentials for backend OTA integration not provisioned. Blocking WI-056/058. Open.
BLK-005 | WI-048 | WI-048, WI-052 | Medium | Resolved | Ravi Chandran | 2026-06-16 | 2026-06-22 | 2026-06-21 | Tool Issue | Sprint 5 | Cybersecurity toolchain (HSM simulator) misconfigured; blocked WI-048 attack surface tests. Fixed by tool team.

## Lists
TIO2 – REFERENCE LISTS (Data Validation Sources)
ProjectStatus | SprintStatus | WorkItemType | Priority | WorkItemStatus | YesNo | ScopeReason | DependencyType | Severity | BlockerStatus | BlockerCategory | Owners | Skills | Sprints | SkillCategory
Active | Not Started | Feature | Critical | Not Started | Yes | Customer Request | Finish-To-Start | Low | Open | Lab Issue | Karthik Subramaniam | AUTOSAR Stack Configuration | Sprint 1 | Architecture
On Hold | In Progress | Story | High | In Progress | No | Technical Debt | Start-To-Start | Medium | In Progress | Hardware / Procurement | Priya Meenakshi | MCAL Driver Integration | Sprint 2 | Development
Completed | Completed | Task | Medium | Completed |  | Regulatory | Finish-To-Finish | High | Resolved | External Team Dependency | Arjun Sundaram | OS Task Scheduling | Sprint 3 | Integration
Cancelled |  | Defect | Low | Blocked |  | Defect |  | Critical | Closed | Tool Issue | Vikram Narayanan | CAN / J1939 Protocol Development | Sprint 4 | Testing
|  | Spike |  | Deferred |  | Enhancement |  |  |  | People | Akshaya Krishnan | COM Stack & Signal Mapping | Sprint 5 | Security
[6 empty] | Other |  |  |  |  | Sandeep Annamalai | CANoe Scripting | Sprint 6 | Delivery
[11 empty] | Divya Rajalakshmi | UDS Diagnostics & DTC Management | Sprint 7
[11 empty] | Meena Balasubramanian | DCM / DEM Module Configuration | Sprint 8
[11 empty] | Ravi Chandran | ASPICE Audit Support
ECU Integration & Gateway Routing
PDU Configuration
Fleet Telemetry
HIL Testing & CANoe Automation
Regression & Integration Testing
OTA Validation
Automotive Cybersecurity (EVITA)
SecOC & Secure Boot
HSM Integration
Agile Delivery & Sprint Tracking
Stakeholder Communication
DoD Governance
OTA Firmware Update Mechanisms
Manifest & Delta Packaging
Backend API Integration